Lambeth Council’s migration experience – case study

Type of data	Digital
LLC system software	Idox TLC
Number of charges	77302

Top 10 lessons learned from Lambeth Council
Click on any item to read more.

Put together a project team from the start, comprising representatives from affected departments, including a senior member of staff and the authorities Project Management Office

Familiarise yourselves with the configuration tools and the Cloud Connector Framework Management Console (Idox users) as early as possible and learn to use these tools in the various staging environments as frequently as possible

Identify data owners for all types of charges, and who is able to make decisions regarding them

Your HMLR Delivery Manager and subject matter experts can offer support; utilise their knowledge of earlier migrations

1. On-board your IT teams as early as possible in the process and ensure that they understand & familiarise themselves with the variety of tools and requirements as early as possible. Also ensure that an officer from your authorities network team makes contact with officers from HMLR’s network team to setup and test the end to end connectivity
2. Prepare your data well in advance if you can; HMLR will let you know their data specification requirements, so that you can check whether you have the mandatory items needed

Seek the advice of other migrated local authorities, particularly those with the same software system

Build robust communication channels early on in the process, using the best tools available

Don’t underestimate the amount of back-and-forth that could be required to resolve issues

Identify changes required to processes and service that the project will have post-go live

HMLR can put you in touch with any of the Lambeth Council or HMLR team if you want to ask further questions: llcproject@landregistry.gov.uk.

Advice for other local authorities

1.This will help establish communication routes, allow you to adopt the well-developed best practice model, utilise the lessons learnt library and speed up the decision-making process

2.It takes some time to familiarise yourself with using the tools and specific processes to follow in relation to self-extract and bulk export LLC data and also to create customised business rules, so build in some time to do this

3.Identifying and informing officers from the professional service areas (Planning, Building Control, Housing etc.) who may be required to play a part in the project, and keeping them aware of what is happening, will keep these channels open to you if a need for information or decisions are identified

4.The technical staff at HMLR have the expertise to assist with creation of business rules, and preparation of data. Your Delivery Manager can mobilise the assistance of subject matter experts as and when you need it

5.IT will be pivotal to extracting, manipulating and ensuring data is securely transmitted from end to end or obtaining data/open connectivity from other systems in the authority, so the sooner they are on side and aware of potential requirements the easier things will be to keep moving

6. The sooner you know what format HMLR require the data to be in, the better it will be in terms of preparation.

7.If you’re stuck for a solution or unsure how to approach a problem, then it makes sense to ask your delivery manager to let you know see if another authority had similar issues, and the contact name of the officer in that authority. You can then make contact with that person to enquire how they managed to find a solution. It may not work totally for your situation, but could provide ideas and options you may not have considered

8.Communication is key. Building defined communication routes and keeping track of everything will speed responses up and help you keep track of progress. If you can, make use of specialist collaboration tools that help simplify this process and provided increased viability. Email alone is not a good enough solution.

9.Getting the answers required may not always be a straightforward as it seems. Getting answers to questions asked on decades old data may require you to involve multiple internal stakeholders.

10.BAU will be different post-migration. Identifying these changes as early as possible, and the impact this might have on staff in other departments is key and will allow you to train staff if required and put changes in place.

Read more about who was involved and how they resolved issues.

Who was involved?

Lambeth Council	HM Land Registry LLC Programme
Gerard Kamath - Business Manager in Legal and Governance	Jo Hoskin / Delivery Manager
Limi Arub – Assistant Business Manager in Legal and Governance	Rod Else / Data Quality Manager
Mike Netley – Senior ICT Officer (DBA)	Richard Evans / Business Analyst
Alison McKane – Director of Legal Services	Mark Griffin / Technical Lead
Jatinder Saggu - Systems Delivery Officer
Tom Brown - Geographic Information Manager (ICT)

Resolving issues

Missing spatial extents

We had to tackle the issue of missing spatial extents, or instances of point data (rather than polygon data). HMLR worked with us to provide candidate polygons, which meant we were not starting from scratch in identifying each extent. They were loaded into the Migration Helper (which was being developed at the time), and it speeded up the process. Now that the dashboard and early data analysis is in place, other local authorities will have early sight of these type of issues.

Missing addresses for charges affecting large areas

HMLR require a geographic description for each charge. For charges such as Conservation Areas which affected multiple properties, we had no single generic description for these charges in Idox TLC. We were able to use the configuration tool supplied by Idox to create a business rule which lifted a useable description from a different part of TLC and used this as a generic description for HMLR’s register. This greatly simplified what would otherwise have been a lengthy task.

Any questions?
llcproject@landregistry.gov.uk