Roles and Responsibilities

Purpose

This document provides an overview of the various functions performed by local authority and HM Land Registry (HMLR) personnel during migration of the Local Land Charges (LLC) service.

Who is it for?

Local authority
Senior Responsible Owner, Operational Lead and Local Land Charges Officer

Local authority

Senior Responsible Owner
Operational Lead
Local Land Charges Officer

Local Authority Functions

GIS
IT
Planning
Legal
Finance

Role	Responsibilities
Senior Responsible Owner	Leads the strategic oversight of the migration / Makes strategic decisions on behalf of the local authority / Ensures the local authority fulfils its obligations to receive transition payments / Ensures the migration is considered in the wider local authority context / Feeds back on progress to all stakeholders including HMLR / Raises awareness of the support infrastructure provided by HMLR
Operational Lead	Primary contact within the local authority / Works closely with the HMLR Delivery Manager / Ensures migration activities delivered to time / Provides detailed insight into the service, people, data and processes / Deploys resource / Engages all necessary support functions as required
Local Land Charges Officer	Undertakes migration activities / Responds to data-related queries / Provides insight into current LLC processes / Continues to deliver the LLC service through migration
IT Lead	Enables extraction of data / Provides information on IT architecture, software and processes / Sets up Secure File Transfer Protocols (SFTP) / Implements system-related upgrades
GIS Officer	Provides information on and access to spatial data
Planning Officer	Provides information on and access to planning data and processes / Responds to data issue enquiries / Effects amendments to local authority data
Legal	Main contact for legal matters including consideration of the Collaboration Agreement and HR-related matters
Finance	Provides information on financial charge-related data and processes / Responds to data issue enquiries

HM Land Registry

Local Authority Delivery Manager

Supporting Functions

Customer Delivery Manager
Business Analyst
Data Quality Analyst
Technical Delivery Manager
Lawyer

Role	Responsibilities
Local Authority Delivery Manager	Main contact within the Programme / Works closely with the local authority Operational Lead / Project manages the end-to-end delivery from pre-migration to go-live / Coordinates with HMLR subject matter expertise
Customer Delivery Manager	Raises awareness of the Local Land Charges service with customers / Leads launch event planning / Account manages volume Local Land Charges customers
Business Analyst	Works with local authorities and suppliers to deliver digitisation and transformation of local authority data / Undertakes analysis of local authority data to determine compatibility with HMLR’s LLC Register / Works with local authority Local Land Charges teams and HMLR Local Authority Delivery Managers to enhance local authority data to meet HMLR’s LLC Register requirements
Data Quality Analyst	Evaluates data output against pre-defined standards and data specifications / Develops and reviews technical solutions to enable standardised quality assessments to be carried out against bulk data sets / Assimilates and reports on output from quality assessments to give assurance quality is being maintained at the correct level
Technical Delivery Manager	Supports local authorities in the extraction of Local Land Charges data / Works closely with local authority IT Leads / Establishes a community of best practice amongst local authorities and other originating authorities / Assists in the engagement with and management of incumbent suppliers / Works closely with the Local Authority Delivery Manager
Lawyer	Provides legal support on policy, commercial and migration matters / Primary Programme contact for Collaboration Agreement queries

Any questions?
llcproject@landregistry.gov.uk